## Compliance Schedule 2018 - 2021
Round 1 (tentative) Compliance Review Program Timeline/Schedule
Priority | Organization | Round 1 Status | 2018-10-01 | 2018-11-01 | 2018-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2019-01-01 | 2019-02-01 | 2019-03-01 | 2019-04-01 | 2019-05-01 | 2019-06-01 | 2019-07-01 | 2019-08-01 | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01
1 | CalVet | complete
2 | CHHS - CDPH | complete
3 | CalPERS | complete
4 | CHHS - CDA | complete
5 | CalFIRE (BA) | complete
6 | CHHS - DHCS (CE) | complete
7 | CHHS - DSH (CE) | complete
8 | CDCR - CCHCS (CE) | targeted
9 | CHHS - CDSS (CE) | targeted
10 | DGS - EDMS (BA) | targeted
11 | CHHS - DDS (CE) | rescheduled
12 | CHHS - OSI (BA / Oversight) | targeted | start | underway | underway | end
13 | CHHS - EMSA (BA) | targeted |  |  |  | start | underway | underway | end
14 | CDCR (CE) | targeted | [6 empty] | start | underway | underway | end
15 | FI$Cal (BA) | targeted | [9 empty] | start | underway | underway | end
16 | SCO (BA/Oversight) | targeted | [12 empty] | start | underway | underway | end
17 | DOJ (BA/Oversight) | targeted | [15 empty] | start | underway | underway | end
18 | CDT (BA) | targeted | [18 empty] | start | underway | underway | end
19 | DGS (BA) | targeted | [21 empty] | start | underway | underway | end
Round 2 (tentative) Compliance Review Program Timeline/Schedule
Priority | Organization | Round 2 Status | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | 2020-08-01 | 2020-09-01 | 2020-10-01 | 2020-11-01 | 2020-12-01 | 2021-01-01 | 2021-02-01 | 2021-03-01 | 2021-04-01 | 2021-05-01 | 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01
1 | CalVet | not started | 2020-10-01: start; 2020-11-01: underway; 2020-12-01: underway; 2021-01-01: end
2 | CHHS - CDPH | not started | 2021-01-01: start; 2021-02-01: underway; 2021-03-01: underway; 2021-04-01: end
3 | CalPERS | not started | 2021-04-01: start; 2021-05-01: underway; 2021-06-01: underway; 2021-07-01: end
4 | CHHS - CDA | not started | 2021-07-01: start; 2021-08-01: underway; 2021-09-01: underway; 2021-10-01: end
5 | CalFIRE (BA) | not started | 2021-10-01: start; 2021-11-01: underway; 2021-12-01: underway
6 | CHHS - DHCS (CE) | not started
7 | CHHS - DSH (CE) | not started
8 | CDCR - CCHCS (CE) | not started
9 | CHHS - CDSS (CE) | not started
10 | DGS - EDMS (BA) | not started
11 | CHHS - DDS (CE) | not started
12 | CHHS - OSI (BA / Oversight) | not started
13 | CHHS - EMSA (BA) | not started
14 | CDCR (CE) | not started
15 | FI$Cal (BA) | not started
16 | SCO (BA/Oversight) | not started
17 | DOJ (BA/Oversight) | not started
18 | CDT (BA) | not started
19 | DGS (BA) | not started